## Sheet1
Stage | Activity | Part of activity | enter information | review information previously entered | program does something with inputted data | do activity in software | do activity outside software and report back | Estimates
Intro
Planning | Project stories |  | tell stories, answer questions about them (questions are same for all projects) | look over stories, simple patterns | program creates bar graphs and other graphs from data just entered (answers to questions about stories) | clustering themes; OR, pairwise comparison (prioritization) of themes |  | 100
| Project aspects (participants, topic, privacy) |  | answer questions about project |  | recommendations about collection venues, anonymity, etc (issue: what to do when answers to questions are changed after recommendations are presented?) |  |  | 20
| Assessment test (optional) |  | answer questions in test from book |  | recommendations about collection venues, anonymity, etc |  |  | 20
| Planning questions |  | fill in answers to questions |  |  |  | discuss and refine | 2
| Synopsis |  | write synopsis |  |  |  | discuss and refine | 2
Collection | Venues |  | possibly a few more questions than in planning section | review answers to project aspects questions again | program pulls up info from earlier entry and displays it; should be recommendations based on info already entered in planning (if not entered yet must enter it now) |  |  | 40
| Prompting questions | Prompting question types | possibly a few more questions than in planning section | review answers to project aspects questions again | program pulls up info from earlier entry and displays it; should be recommendations based on info already entered in planning (if not entered yet must enter it now) |  |  | 40
|  | Theme-based prompting questions | write theme based questtions | bring back info from theming exercise in planning | program pulls up info from earlier entry and displays it |  | discuss and refine | 20
|  | Draft prompting questions | enter questions |  |  |  | discuss and refine | 2
|  | Feedback on prompting questions | enter annotations on questions based on pilot testing - confusing, upsetting, etc |  |  |  | discuss and refine | 2
| Interpretation questions | Interpretation question types | possibly a few more questions than in planning section | review answers to project aspects questions again | program pulls up info from earlier entry and displays it; should be recommendations based on info already entered in planning (if not entered yet must enter it now) |  |  | 40
|  | Theme-based interpretation questions | write theme based questtions | bring back info from theming exercise in planning | program pulls up info from earlier entry and displays it |  | discuss and refine | 20
|  | Draft interpretation questions | enter questions |  |  |  | discuss and refine | 2
|  | Feedback on interpretation questions | enter annotations on questions based on pilot testing - confusing, upsetting, etc |  |  |  | discuss and refine | 2
| Questions about people | People question types | possibly a few more questions than in planning section | review answers to project aspects questions again | program pulls up info from earlier entry and displays it; should be recommendations based on info already entered in planning (if not entered yet must enter it now) |  | discuss and refine | 40
|  | Draft people questions | enter questions |  |  |  | discuss and refine | 2
|  | Feedback on people questions | [5 empty] | 2
| Designing the question form |  | add info to make it into a form (what the project is about, etc) | look over questions previously chosen/written |  | move questions around by dragging | read to people, record reactions | 40
|  |  | choose questions from built-in library |  | retrieve and show library questions
|  |  | export and import questions to files |  | save and load questions
| Story collection data entry |  |  |  | display question form to people taking survey, collect responses |  |  | 200
print question forms - or export to PDF or HTML - to print for use in face-to-face settings
Catalysis | Preparing data |  |  |  | no need to fix data as it will come directly from survey as specified (no other option) |  |  | 0
| Verifying data integrity |  |  | look over sample stories and data to confirm | prepare samples for display |  |  | 5
| Scoping exploration |  | scope set by user changing only a few options as to how much depth to use |  |  |  |  | 20
| Producing results |  |  | user looks at graphs; also need way to theme stories using some kind of interface | all results produced by program; user only sees most significant results (based on statistics) in graphs; program prepares graphs (like NarraCat) |  |  | 200
| Accumulating observations |  | user writes sentences to describe observations | user chooses from most significant results to find remarkable observations; user can also change significance thresholds |  |  |  | 5
| Interpretating and exploring observations |  | enter 2 or more interpretations; give them short names (not much exploration at this point) | look over previous pages of observations and interpretations (and possibly ideas); look over stories using some kind of story browser (where you can choose subsets of stories by question answer) |  |  |  | 13
| Clustering interpretations |  |  | user looks at short names of interpretations |  | cluster written interpretation names |  | 20
| Preparing report |  |  |  | report should be automatic based on user-chosen (remarkable) results, observations, interpretations (possibly ideas) |  |  | 13
Sensemaking | Planning sessions |  | choose how many sessions, who to invite, etc |  | recommendations based on answers to questions during planning phase |  |  | 20
| Designing session agenda |  | choose segments, describe |  | recommendations based on answers to questions during planning phase | drag segments around |  | 20
| Real-time session help |  |  |  | could run timer and put up instructions for agenda |  |  | might not do?
| Recording the session |  | can input audio, video, photos |  |  |  |  | 20
| Post-session review |  | answer questions |  |  |  | discuss | 2
| Sensemaking report |  |  |  | auto generated based on all info entered in sensemaking step |  |  | 13
Intervention | Choose/design interventions |  | answer questions |  | recommendations based on answers to questions and during planning phase |  |  | 20
| Post-intervention review |  | describe interventions |  |  |  |  | 2
| Intervention report |  |  |  | based on all things entered in intervention phase |  |  | 13
Return | Gather feedback |  | enter things people said, observations |  |  |  |  | 2
| Review meeting |  | answer review questions; enter final observations | review all things entered | program will select from all info entered and display appropriate info for project review |  | discuss | 20
| Responding to requests |  | enter requests and what was done in response |  |  |  | help people, report back | 20
| Return report |  |  |  | based on all things entered in return phase |  |  | 13
| Steering committee presentation |  | prepare brief report for committee | review whole project info |  |  |  | 20
| Project report |  |  |  | full report on everything entered and generated in whole project |  |  | 20
Infrastructure tasks | Form filling | [6 empty] | 5
| Data storage and retrieval | [6 empty] | 40
| Rule based recommendations generation | [6 empty] | 20
| Pairwise comparison for ranking | [6 empty] | 13
| Dragging items in lists | [6 empty] | 5
| Clustering in 2D | [6 empty] | 5
| Multi-user clustering | [6 empty] | 40
| Statistics | [6 empty] | 20
| Graphing | [6 empty] | 13
| Bringing previously entered data forward for display | [6 empty] | 20
| Displaying instructions | [6 empty] | 5
| Links to book (online) | [6 empty] | 40
| Uploading images | [6 empty] | 5
| Uploading audio | [6 empty] | 20
| Uploading video | [6 empty] | 40
| Comments on documents | [6 empty] | 13
| User roles and permssions | [6 empty] | 5
| Generic way putting in questions as html | [6 empty] | 20
| Theming interface (not clustering) | [6 empty] | 20